## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Daily
| Current Week | Daily - Current Week
| Current Week-1 | Daily - Current Week-1
| “All Drawings from the Sheet” | Daily - Drawings
Weekly
| Current Week | Weekly - Current Week
Blank
| Date | Blank - Date
| Current Week | Blank - Current Week
| “All Drawings from the Sheet” | Blank - Drawings

## Daily - Current Week
WEEK | PRIMARY OBJECTIVE | SECONDARY | TERCIARY | NOTES
6 | Official meeting 1 |  |  | First Officially Scheduled meeting
7 | Certification Research Finished | Elementary Schools/ Programs decided on | Professors and potential advisors contacted | By end of meeting
8 | Preliminary outreach done | Teaching certified/ at least volunteer certified | Discussions with schools in progress
9 | Initial Curriculum Development | Scheduling with schools in progress | Budget application (hopefully) approved
10 | “team leaders” begin developing plans | Scheduling with schools finished | First few classes prepped for and finalized for next quarter
FINALS | ace finals! | Clear plan for next quarter

## Daily - Current Week-1
Curriculum Development Meeting | Outreach meeting | CD/Outreach collaboration | Business Meeting
New ideas (independent work) | Create next week’s class |  | Schedule next classes
Research | Base classes off of meeting with C.D. |  | Reach out to more schools
Report to meeting/ collaborate | Create class outline and practice teaching skills |  | Organize and facilitate this process ^^^

## Daily - Drawings
Superclass Outreach Schedule
Winter 2017
Rough idea of ‘team meetings’; plans and ideas to be developed

## Weekly - Current Week
WEEK # | SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
1
2
3
4
5
6
7
8
9
10
11
Weekly Schedule

## Blank - Date
2016-10-25

## Blank - Current Week
TIME | SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY

## Blank - Drawings
Schedule